## Reconciled_Root_Cause_Register
Issue ID | Phase | Severity | Subsystem | Observed Symptom / Original Behaviour | Root Cause Evidence (File & Line) | Root Cause Mechanism | Discrepancy / Downstream Impact | Baseline Result | Corrected Result / Proposed Fix | Test Procedure & Run ID | Acceptance Criterion | Reconciled Audit Status | Remaining Limitations
ISSUE-00 | Phase 1 | HIGH (Audit Governance) | Project Provenance & Baseline | Multiple disparate simulation runs, undocumented stop times (0.2s vs 0.4s vs 0.5s), unhashed files, and conflicting audit metrics. | Root scripts vs Simulation Logs/EV_RUN_* folders, BASELINE_FILE_MANIFEST.csv | Lack of formal file hash manifests and run provenance tracking allowed results from truncated runs to be compared directly against full-load runs. | Conflicting audit conclusions and unrepeatable verification claims. | Inconsistent metrics cited across legacy reports. | Established single primary baseline on EV_RUN_20261021_161504 (t_stop = 0.40s) with complete MD5 file manifest (BASELINE_FILE_MANIFEST.csv), configuration sheet (BASELINE_RUN_CONFIGURATION.txt), and inventory document (BASELINE_INVENTORY.md). | Inspection & MD5 hash computation; Run ID EV_RUN_20261021_161504 | Every numerical result traceable to an identified run ID, file hash, and configuration. | VERIFIED | Legacy runs prior to 21-Oct-2026 lack comprehensive per-cell raw logs.
ISSUE-01 | Phase 3 | CRITICAL (Fixed in V7) | BLDC Motor Back-EMF & Torque | Motor generated only 0.038 N*m/A (35% of rated torque) and stalled at ~600 RPM under load. | BLDCSpeedControlData.m (L40-44), BLDCSpeedControl_EV_Layout_v2/BLDC Motor (SID 2178) | Simscape trapezoidal BLDC block back-EMF parameter table expects phase-to-neutral flat-top amplitude. Legacy script set Ke_ph = Kt/2 = 0.0535 V*s/rad, ignoring internal block multiplier kappa ~ 0.71-0.72. | Motor could not accelerate or maintain speed; current hit limiter ceiling; false motor failure. | Low torque (0.038 N*m/A), motor stall under rated load. | Calibrated back-EMF constant using kappa = 0.72, yielding Ke_ph = 0.1486 V*s/rad. Simulation produces steady-state Kt = 0.1077 N*m/A (+0.65% vs 0.107 datasheet). | Full load test (3.18 Nm, 2950 RPM); Run ID EV_RUN_20261021_161504 | Steady-state Kt within +/- 5% of 0.107 N*m/A. | VERIFIED | Back-EMF flat-top shape assumes idealized 120-deg trapezoid; real motor has small harmonic distortion.
ISSUE-02 | Phase 3 | HIGH (Active Warning) | Drivetrain Acceleration | Console warning BLDC:rampAboveCont: Ramp 13000 rpm/s needs 30.4 A > I_cont = 30 A. | BLDCSpeedControlData.m (L71, L127-137), EV_RUN_20261021_161504 command log | Speed reference ramp of 13000 rpm/s (alpha = 1361.36 rad/s^2) with total reflected inertia J_tot = 0.00239 kg*m^2 requires acceleration current I_accel = J_tot * alpha / Kt = 30.37 A, exceeding continuous 30 A rating. | Continuous rating (30 A) is exceeded during no-load acceleration, inducing premature thermal stress and depleting I^2*t limiter budget before load begins. | Active warning triggered in console during startup. | Reconciled engineering operation: Nanotec APBA80L048030 datasheet permits peak current up to 90 A catalog / 45 A controller limit for transient acceleration. The I^2*t thermal limiter budget (1125 A^2*s) is respected (actual I^2*t = 10.28 A^2*s, check VV-022 PASS). For strictly warning-free operation, reduce ramp to <= 11500 rpm/s (demands 26.8 A). | Startup acceleration test (0 to 0.227s); Run ID EV_RUN_20261021_161504 | Acceleration current protected by peak limiter (45 A) and I^2*t budget. | CALCULATED | Aggressive ramp slightly reduces thermal headroom if load step is applied immediately.
ISSUE-03 | Phase 3 | MEDIUM (Metric Discrepancy) | Current Metrics (VV-004 vs VV-008) | Apparent conflict between steady-state current (30.3 - 32.8 A, FAIL/WARN) and RMS current (26.41 - 28.63 A, PASS). | EV_DAQ_Builder_V7.m (L2491-2495), 04_VV_Results.xlsx (VV-004 vs VV-008 vs VV-023) | Different operating windows and mathematical metrics on the same signal: 1) VV-004 computes whole-run RMS (0 to 0.4s) where low-current startup ramp lowers RMS to 28.63 A. 2) VV-008 computes window mean of last 10% (0.36 to 0.40s) where 1 kW load is applied. 3) Rated load (3.18 Nm) requires 29.72 A; mechanical friction damping (B = 0.001 N*m*s/rad adds 0.309 Nm) pushes gross current to 32.6 A peak / 30.3 A average. | User confusion over whether current limit is respected; false alarm of motor overload. | Disagreement between whole-run RMS (PASS) and steady-state average (FAIL). | Reconciled metric definitions across windows. Verified that whole-run RMS (28.63 A <= 30 A) PASSES, while steady-state full load (30.3 A) slightly exceeds 30 A due to external load + internal friction damping. | Whole-run vs hold window evaluation; Run ID EV_RUN_20261021_161504 | Window boundaries and metrics explicitly documented. | VERIFIED | Motor operates at 101% of continuous thermal rating under full 3.18 Nm load + friction; requires 5% load de-rating for continuous infinite-duration operation.
ISSUE-04 | Phase 3 | HIGH (Operational Defect) | Run Duration Truncation / Schedule | Simulating with t_stop <= 0.20 s causes VV-001 (speed) and VV-018 (power) to FAIL (speed = 2583 RPM, power = 0 W). | RunAll.m (L120-130), EV_RUN_20261021_172910 04_VV_Results.xlsx | Speed reference ramp takes 2950 / 13000 = 0.227 s to reach 2950 RPM. Load profile Test_1 ramps from 0 to 3.18 Nm between 0.230 s and 0.280 s. Stopping at 0.20 s truncates simulation before speed settles or load is applied. | Generates false-negative test failures and invalid data archives. | False-negative failures on speed and power in 0.20s runs. | Minimum simulation stop time constraint enforced: t_stop >= 0.40 s for full-load acceptance testing. Short runs (<= 0.20 s) restricted to startup diagnostic testing only. | Comparison between 0.20s and 0.40s runs; Run IDs EV_RUN_20261021_172910 vs 161504 | All full-load acceptance tests executed with t_stop >= 0.40 s. | VERIFIED | 0.40s run provides 120 ms of post-load steady-state; extended 2.0s run recommended for long-term thermal analysis.
ISSUE-05 | Phase 4 | MEDIUM (Measurement Limit) | DC-Link Current & Power Balance | Instantaneous power balance Pdc / Pbatt spikes up to 1.05 - 1.11, appearing to violate energy conservation. | BLDCSpeedControl_EV_Layout_v2 (SID 2248, 2314), 04_VV_Results.xlsx (VV-012) | The model contains NO physical current sensor on the DC-link bus. Block Meas V measures only voltage. Logged current Idc_f is an internal controller estimate: max(¦i_abc¦) passed through a 2 ms low-pass filter. Filter lag and reactive LC energy storage cause Vdc * Idc_f to dynamically lead/lag battery power. | Instantaneous DC-link power balance cannot be treated as physical sensor proof. False claim of direct measurement. | Apparent power violation during transitions (ratio up to 1.11, VV-012 FAIL at 1.026). | Formally reclassified and labeled as Estimated DC Power. Verified that average steady-state efficiency (95.96%) and ramp-phase power balance (0.9746, VV-024 PASS) are physically consistent. | Signal path inspection & power balance calculation; Run ID EV_RUN_20261021_161504 | Clear distinction between physical measurement and controller estimation. | VERIFIED | Direct DC bus shunt/Hall sensor required for true physical measurement validation.
ISSUE-06 | Phase 2 | HIGH (Model Defect) | SysID Model Signal Mapping | Saved root SysID model EV_BlackBox_SysID.mat duplicates RPM as both input and output; does NOT predict battery current. | Root EV_BlackBox_SysID.mat (labels_u = [RPM_rpm, Idc_f_A], labels_y = [Vbatt_V, SOC, RPM_rpm]) | Legacy SysID script designated RPM as an input (u1) and simultaneously as an output (y3). It did NOT include Ibatt as an output. Predicting an input as its own output forces an identity state and degrades battery identification. | Poor validation fit; model unsuited for battery digital twin state estimation. | Flawed legacy model with duplicate RPM and missing Ibatt. | Resolved and regenerated in EV_BlackBox_SysID_FINAL.mat: labels_u = [RPM, MotorCurrent], labels_y = [Vbatt_V, Ibatt_A]. Duplicated RPM removed; battery current included; SOC delegated to Coulomb counting. | Model inspection and variable verification; EV_BlackBox_SysID_FINAL.mat | Saved MAT file labels match estimation script and project objectives. | VERIFIED | Temperature excluded due to lack of thermal sensor/model.
ISSUE-07 | Phase 2 | MEDIUM (Fixed in V7 & Proven) | SysID Fit Calculation & Negative Fit | Older SysID report printed fit = 2034946643217408.2% and recent run showed -2158.9% fit. | EV_SysID_Auto.m (L104), EV_RUN_20261021_161504 SysID report | 1) Legacy bug: MATLAB compare() returns initial state x0 as 3rd output; legacy code read 3rd output instead of 2nd (NRMSE fit %). Fixed in V7. 2) Negative fit (-2158.9%): validation dataset (0.28 to 0.40s) is in pure steady state where ground-truth voltage variance collapses to 0.000234 V^2 (sigma = 0.0153 V). NRMSE denominator collapses to near zero, amplifying a tiny 0.344 V error into a -2158% metric. | Misleading validation reports; invalid assessment of model quality. | Fit reported as -2158.9% despite low absolute error. | Bug fix verified. Negative fit proven mathematically to be a variance collapse artifact. Absolute physical error verified: Voltage RMSE = 0.3441 V (0.63% relative error), MAE = 0.3120 V. | Subspace simulation & variance breakdown; Run ID EV_RUN_20261021_161504 | Accurate error calculation without artificial positive fit claims. | VERIFIED | NRMSE metric should be supplemented with RMSE/MAE on steady-state intervals.
ISSUE-08 | Phase 4 | MEDIUM (Modeling Gap) | Battery Cell Resistance Modeling | Modeled pack resistance is ~0.011 Ohm, representative of a 27 Ah cell template rather than an authentic 5 Ah 21700 cell. | +Batteries2/ParallelAssemblyType1.ssc (L20-22), BLDCSpeedControlData.m (L47-51), Samsung 50E datasheet | Pack was built in Simscape Battery Builder using a 27 Ah cell template (R0 ~ 8.5 mOhm). When cell capacity was overridden to AHCell = 5 Ah, the internal resistance lookup table was not scaled up. Real 5 Ah 21700 cells (Samsung 50E) have R_DC ~ 20 - 30 mOhm. | Simulation underestimates battery terminal voltage sag (0.29 V modeled vs 0.75 - 1.0 V real under 26 A discharge) and underestimates battery Joule heating. | Underestimated voltage sag (0.29V modeled). | Discrepancy documented and modeled vs datasheet values compared in Datasheet_vs_Simulation_Values.xlsx. Active model retained with documented caveat to avoid breaking validated V7 baseline. | Datasheet impedance comparison & Simscape SSC inspection | Documented parameter provenance and sag discrepancy analysis. | REPORTED | Re-synthesis in Simscape Battery Builder required to insert Samsung 50E lookup table.
ISSUE-09 | Phase 4 | LOW (Missing Telemetry) | Missing Reference & Thermal Signals | rpm_ref and cell temperature are reported as NOT_AVAILABLE in signal map and Black Box archive. | BLDCSpeedControl_EV_Layout_v2.slx, EV_DAQ_Builder_V7.m (signal map L2350) | The model does not contain a thermal equivalent circuit for cell heat dissipation, and the reference speed ramp signal is not routed to a To Workspace logger block. | Inability to log or cross-validate battery thermal runaway or reference tracking error directly from Black Box archive. | Signals marked NOT_AVAILABLE. | Honest reporting confirmed: NOT_AVAILABLE is reported without fabricating synthetic data. Verified in EV_SysID_Signal_Mapping.md. | Signal map inspection in EV_DAQ_Builder_V7.m | Clear reporting of signal availability without fabrication. | VERIFIED | Reference signal should be wired to logger in future model revision.
ISSUE-10 | Phase 6 | HIGH (Architecture Classification) | Closed-Loop Digital Twin Integration | Project described as a real-time digital twin, but state-space model is executed offline only; not connected in closed-loop to Simulink plant. | BLDCSpeedControl_EV_Layout_v2.slx, EVTWIN_Project_Report.docx (Section 3.2) | The project has achieved Digital Shadow (Level 2: unidirectional data flow from simulation to DAQ/SysID). Closed-Loop Digital Twin (Level 3: bidirectional feedback where model estimates influence control) is not yet implemented. | The project does not currently operate as a real-time digital twin controlling the vehicle. | Unsubstantiated claim of production readiness. | Claim of production readiness retracted. Formally classified as Validated Level 2 Digital Shadow. Architecture documented in EV_Digital_Twin_FINAL_AUDIT.md. | Simulink diagram architecture inspection | Report accurately defines twin architecture without inflated claims. | VERIFIED | Real-time closed-loop feedback reserved for future work.
ISSUE-11 | Phase 3 | MEDIUM (Parameter Mismatch) | Motor Stator Resistance & Inductance | Simulink model phase resistance Rs = 0.1 Ohm is 4.65x higher than datasheet (0.0215 Ohm phase). | BLDCSpeedControlData.m (L32-34), Nanotec APBA80L048030-E datasheet | Datasheet specifies line-to-line resistance R_ll = 0.043 Ohm (Wye-connected -> R_phase = 0.0215 Ohm) and L_ll = 0.21 mH. Model uses legacy MathWorks values Rs = 0.1 Ohm (R_ll = 0.20 Ohm) and Ls = 80 uH, Ms = 10 uH (L_ll = 0.14 mH). | Overestimates motor copper losses (3 * I^2 * Rs) and thermal dissipation by ~4.6x; underestimates peak electrical efficiency. | Modeled Rs = 0.10 Ohm vs datasheet R_phase = 0.0215 Ohm. | Reconciled and documented in Datasheet_vs_Simulation_Values.xlsx and BASELINE_INVENTORY.md. Retained in baseline to preserve tuned PI controller stability. | Datasheet comparison and loss calculation | Exact parameter values and conversion equations documented. | CALCULATED | Updating Rs in Simulink requires re-tuning PI speed/current controller gains.
ISSUE-12 | Phase 2 | MEDIUM (Architecture Governance) | Confirm Model Order and Sample Time | Root model used six states, whereas newer estimation script selected two states. | EV_SysID_Auto.m, root EV_BlackBox_SysID.mat, EV_BlackBox_SysID_FINAL_REPORT.txt | Order 6 suffered from severe over-parameterization on 0.4s run, causing ill-conditioned matrices. Order 2 captures the dominant battery dynamics stably with minimal validation error. | Disagreement between legacy report and active estimation script. | Model order inconsistency (nx=6 vs nx=2). | Confirmed nx = 2 and Ts = 1 ms based on order sweep (nx = 1..6) and pole stability (¦lambda_1¦ = 0.9890, ¦lambda_2¦ = 0.2522 < 1). Documented in EV_BlackBox_SysID_FINAL_REPORT.txt. | Order sweep nx=1..6; Run ID EV_RUN_20261021_161504 | Unified model order and sample time across all files and reports. | VERIFIED | Higher-order electrochemical diffusion requires longer multi-minute drive cycles.
ISSUE-13 | Phase 3 | HIGH (Operational Rule) | Simulation Stop-Time & Test Schedule | A 0.20-second run ends before the reported 0.227-second speed ramp completion and 0.28-second load ramp completion. | RunAll.m, EV_LastStopTime.txt, EV_RUN_20261021_172910 | Test schedule has distinct dynamic phases: Startup (0-0.05s), Speed ramp (0-0.227s), Load ramp (0.230-0.280s), and Steady-state hold (0.280-0.400s+). Tests ending before 0.28s fail to apply full load. | Invalid validation data and false-negative test classifications. | Premature cutoff in 0.20s runs. | Enforced minimum stop time rule: t_stop >= 0.40 s for full-load acceptance testing. Established distinct test classifications: Startup, Acceleration, Load-step, and Steady-state. | Test duration audit across Simulation Logs | Test runner enforces minimum stop times per test classification. | VERIFIED | Extended 2.0s run recommended for long-term thermal analysis.
ISSUE-14 | Phase 4 | MEDIUM (Sign & Unit Convention) | Battery Voltage, Capacity, SOC & Signs | Potential confusion between nominal (48.1V) and max (54.6V) voltage, Simscape negative current vs engineering positive discharge, and SOC integration accuracy. | Simscape Battery pack, EV_DAQ_Builder_V7.m (L2380-2395) | Simscape uses passive sign convention (inward current positive = charging), requiring sign inversion for EV discharge engineering convention. | Inconsistent sign conventions across scripts and potential SOC drift. | Potential sign confusion. | Verified 13S10P topology (130 cells, 50 Ah capacity). Confirmed sign conversion in DAQ (abs(BatteryCurrent)). Verified Coulomb counting accuracy (ratio = 0.985, VV-011 PASS). | Sign and integration verification; Run ID EV_RUN_20261021_161504 | Consistent voltage, capacity, and current convention across all outputs. | VERIFIED | Cell self-discharge not modeled over 0.4s window.
ISSUE-15 | Phase 5 | MEDIUM (Signal Processing) | DAQ Pipeline & Time Alignment | PWM switching ripple and variable-step solver outputs created noisy raw data with non-uniform time steps. | EV_DAQ_Builder_V7.m (L2300-2450), Raw_Archive files | High-frequency inverter switching (10 kHz) introduces massive ripple that distorts steady-state averages if not filtered uniformly. | Raw simulation outputs unsuitable for black-box system identification. | Noisy variable-step raw data. | Verified 1 ms moving-window uniform resampling and ripple averaging in EV_DAQ_Builder_V7.m. Checked for zero NaNs, zero dropped samples, and exact column mapping. | DAQ script inspection & dataset verification; EV_DAQ_Clean_6_04.csv | Unambiguous 1 ms time base, zero NaNs, documented cleaning manifest. | VERIFIED | 1 ms window limits identification bandwidth to <= 500 Hz.
ISSUE-16 | Phase 5 | HIGH (Quality Assurance) | Rebuild & Verify V&V Checks | 3 checks failed (VV-008, VV-012, VV-023) causing overall test run to report FAIL, with unclear diagnostic explanation. | 04_VV_Results.xlsx, EV_DAQ_Builder_V7.m (L2480-2600) | Zero-tolerance thresholds on steady-state continuous current (30 A limit vs 30.3 A actual) and power ratio (1.02 limit vs 1.026 actual) triggered hard failures due to drivetrain mechanical friction and controller filter lag. | Test runner reported overall FAIL, raising unwarranted doubts about simulation validity. | 3 failing checks in baseline run. | All 25 checks systematically audited, formulas and intervals documented in EV_VV_FINAL_RESULTS.xlsx. 21 checks PASS; 3 checks FAIL due to documented mechanical friction and filter lag. | V&V recalculation across all 25 checks; Run ID EV_RUN_20261021_161504 | Every status supported by a reproducible calculation. | VERIFIED | Re-tuning thresholds or load scaling required for 100% green dashboard.
ISSUE-17 | Phase 7 | HIGH (Documentation Integrity) | Synchronize Audit Report & Excel Register | Discrepancies between narrative markdown report and Excel register in issue numbering, severities, and metrics. | EV_Digital_Twin_COMPLETE_ROOT_CAUSE_AUDIT.md vs EV_Digital_Twin_ROOT_CAUSE_REGISTER.xlsx | Independent updates to different documents caused desynchronization of issue IDs and statuses. | Inconsistent documentation confusing stakeholders and reviewers. | Desynchronized issue lists. | 100% synchronization established across all 18 issues (ISSUE-00 to ISSUE-17) across EV_Digital_Twin_ROOT_CAUSE_REGISTER_FINAL.xlsx, EV_Digital_Twin_FINAL_AUDIT.md, EV_Digital_Twin_ROOT_CAUSE_REGISTER.xlsx, and EV_Digital_Twin_COMPLETE_ROOT_CAUSE_AUDIT.md. | Cross-document reconciliation & schema matching | Exact 1-to-1 matching of IDs, severities, descriptions, and statuses. | VERIFIED | None.