## Reconciled_Root_Cause_Register
Issue ID | Phase | Severity | Subsystem | Observed Symptom / Original Behaviour | Exact File, Function, Block, or Parameter Responsible | Root Cause Demonstrated by Inspection / Test | Discrepancy / Downstream Impact | Before-and-After Measurements | Corrective Change Made | Existing Test-Case ID & Execution Procedure | Acceptance Threshold and Actual Result | Final Status (PASS, FAIL, WARN, NOT VERIFIED) | Remaining Limitations
ISSUE-00 | Phase 1 | HIGH (Audit Governance) | Project Provenance & Baseline | Multiple disparate simulation runs, undocumented stop times (0.2s vs 0.4s vs 0.5s), unhashed files, and conflicting audit metrics. | RunAll.m, BASELINE_FILE_MANIFEST.csv, BASELINE_RUN_CONFIGURATION.txt, BASELINE_INVENTORY.md, Simulation Logs/EV_RUN_* | Lack of formal file hash manifests and run provenance tracking allowed results from truncated runs to be compared directly against full-load runs. | Conflicting audit conclusions and unrepeatable verification claims. | Before: Inconsistent metrics cited across legacy reports with undefined run IDs. After: 100% of numerical results traceable to run EV_RUN_20261021_161504 (t_stop = 0.400 s, 401 samples, MD5 verified). | Established single primary baseline on EV_RUN_20261021_161504 (t_stop = 0.40s) with complete MD5 file manifest (BASELINE_FILE_MANIFEST.csv), configuration sheet, and inventory document. | TC-INIT-01; Inspection & MD5 hash computation on EV_RUN_20261021_161504 | Threshold: All files hashed and single run ID established. Actual: All 26 core files hashed with MD5; Run ID EV_RUN_20261021_161504 established. | PASS | Legacy runs prior to 21-Oct-2026 lack comprehensive per-cell raw logs.
ISSUE-01 | Phase 3 | CRITICAL (Fixed in V7) | BLDC Motor Back-EMF & Torque | Motor generated only 0.038 N*m/A (35% of rated torque) and stalled at ~600 RPM under load. | BLDCSpeedControlData.m (L40-44), Simscape BLDC Block SID 2178 (ee.electromech.pmsm.pm_rotor.bldc.abc), parameter Ke_ph | Simscape trapezoidal BLDC block back-EMF parameter table expects phase-to-neutral flat-top amplitude. Legacy script set Ke_ph = Kt/2 = 0.0535 V*s/rad, ignoring internal block multiplier kappa ~ 0.72. | Motor could not accelerate or maintain speed; current hit limiter ceiling; false motor failure. | Before: Kt = 0.038 N*m/A (stalled at ~600 RPM). After: Kt = 0.1077 N*m/A (+0.65% vs 0.107 datasheet), speed tracks 2950.44 RPM. | Calibrated back-EMF constant using kappa = 0.72, yielding Ke_ph = 0.1486 V*s/rad in BLDCSpeedControlData.m. | VV-019; Full load simulation (3.18 Nm, 2950 RPM); Run ID EV_RUN_20261021_161504 | Threshold: 0.10165 <= Kt <= 0.11235 N*m/A (+/- 5%). Actual: 0.1077 N*m/A. | PASS | Back-EMF flat-top shape assumes idealized 120-deg trapezoid; physical motor exhibits minor harmonic distortion.
ISSUE-02 | Phase 3 | HIGH (Active Warning) | Drivetrain Acceleration | Console warning BLDC:rampAboveCont: Ramp 13000 rpm/s needs 30.4 A > I_cont = 30 A. | BLDCSpeedControlData.m (L71, L127-137), speed ramp rate parameter | Speed reference ramp of 13000 rpm/s (alpha = 1361.36 rad/s^2) with reflected vehicle inertia J_tot = 0.00239 kg*m^2 requires acceleration current I_accel = J_tot * alpha / Kt = 30.37 A, exceeding continuous 30 A rating. | Continuous rating (30 A) exceeded during no-load acceleration, triggering active warning in console. | Before: Console warning triggered; unverified whether overload damaged motor. After: Actual I^2t = 10.28 A^2*s (<1% of allowable 1125 A^2*s budget, VV-022 PASS). | Reconciled engineering operation against Nanotec datasheet which permits peak current up to 90 A catalog / 45 A controller limit for transient acceleration. Verified I^2t thermal limiter budget (1125 A^2*s) is respected. | VV-022; Evaluate int(max(I^2 - I_cont^2, 0) dt) over acceleration (0 to 0.227s); Run ID EV_RUN_20261021_161504 | Threshold: I^2t <= 1125 A^2*s. Actual: 10.28 A^2*s (0.91% of budget used). | WARN | Aggressive ramp slightly reduces thermal headroom if load step is applied immediately during acceleration.
ISSUE-03 | Phase 3 | MEDIUM (Reconciled Metrics) | Current Metrics (VV-004 vs VV-008) | Disagreement between whole-run RMS current (28.63 A, reported PASS) and steady-state average current (30.30 A, reported FAIL). | EV_DAQ_Builder_V7.m (checks VV-004 vs VV-008), EV_VV_FINAL_RESULTS.xlsx | Different operating windows and mathematical metrics: Whole-run RMS (0 to 0.400 s) averages lower startup current (18.9 A) with steady load, yielding 28.63 A. Steady-state hold window (0.360 to 0.400 s) reflects full 1 kW load plus drivetrain damping friction (B = 0.001 N*m*s/rad adding 0.309 Nm gross torque), drawing 30.30 A (+0.30 A above 30 A rating). | Confusion whether motor operates within thermal limits under continuous operation. | Before: Unreconciled metrics (confusion whether motor passed or failed). After: Whole-run RMS = 28.63 A (PASS); Steady-state hold mean = 30.30 A (FAIL, +1.0% above 30 A). | Reconciled metric definitions across specific windows and documented exact formulas. Preserved VV-008 as FAIL to honestly reflect physical powertrain friction margin. | VV-004 & VV-008; Evaluate RMS on [0, 0.400]s and mean on [0.360, 0.400]s; Run ID EV_RUN_20261021_161504 | Threshold: I <= 30.0 A. Actual: Whole-run RMS = 28.63 A (PASS); Steady-state mean = 30.30 A (FAIL). | FAIL | To achieve steady-state current <= 30.0 A, external load torque must be reduced from 3.18 Nm to 2.87 Nm or bearing friction must be lowered.
ISSUE-04 | Phase 3 | HIGH (Schedule Integrity) | Run Duration Truncation / Schedule | False-negative failures on speed tracking and power in 0.20s runs. | RunAll.m, BLDCSpeedControlData.m, EV_LastStopTime.txt | Speed reference ramp takes 2950 / 13000 = 0.227 s, and load torque ramp finishes at 0.280 s. Truncating simulation at 0.20 s evaluated transient startup as steady state. | 0.20s runs failed steady-state checks, misidentifying a duration problem as a plant failure. | Before: t_stop = 0.20 s (terminated before load ramp; 201 samples). After: t_stop = 0.400 s (401 samples; full speed ramp, load ramp, and 120 ms steady hold). | Added minimum stop-time enforcement (t_stop >= 0.350 s; benchmark 0.400 s) in RunAll.m and set default t_stop = 0.4 s in BLDCSpeedControlData.m. | VV-000; Verify simulation duration t_stop >= 0.400 s and sample count N >= 401; Run ID EV_RUN_20261021_161504 | Threshold: t_stop >= 0.400 s. Actual: 0.400 s (401 samples). | PASS | Benchmark duration is 0.400 s; multi-second thermal runs require separate batch script.
ISSUE-05 | Phase 3 | MEDIUM (Measurement Artifact) | DC-Link Current & Power Balance | Check VV-012 reported FAIL with power balance ratio 1.026 > 1.02. | BLDCSpeedControl_EV_Layout_v2.slx (Inverter subsystem), EV_DAQ_Builder_V7.m (check VV-012) | No physical current sensor exists on the DC bus; the signal Idc_f is an internal controller estimate (max(¦i_abc¦) filtered by a 2 ms low-pass filter). The 2 ms phase lag during acceleration causes transient power ratios up to 1.026. | Apparent violation of energy conservation across the DC link. | Before: Ratio = 1.026 cited without explanation. After: Reconciled as 2 ms filter phase lag artifact; steady-state efficiency verified at 78.94% (VV-009 PASS). | Formally reclassified and labeled signal as Estimated DC Power. Verified that steady-state power conversion efficiency is 78.94% (VV-009 PASS) and ramp-phase power balance is 0.9746 (VV-024 PASS). Preserved VV-012 FAIL as documented filter artifact. | VV-012 & VV-024; Compute mean(¦Vdc*Idc¦) / mean(¦Vbat*Ibat¦); Run ID EV_RUN_20261021_161504 | Threshold: 0.85 <= Ratio <= 1.02. Actual: 1.026 (FAIL on VV-012); 0.9746 (PASS on VV-024). | FAIL | Direct DC bus shunt or Hall sensor required for true physical measurement validation.
ISSUE-06 | Phase 2 | CRITICAL (Model Architecture) | SysID Model Signal Mapping | Legacy root model EV_BlackBox_SysID.mat duplicated RPM as both input and output while omitting battery current. | EV_SysID_Auto.m, EV_BlackBox_SysID.mat, EV_BlackBox_SysID_FINAL.mat | Flawed signal indexing in legacy script allocated inputs u = [RPM, Idc_f] and outputs y = [Vbatt, SOC, RPM]. Modeling RPM as both input and output wasted state capacity. | State estimator learned a trivial feedthrough, corrupting battery state estimation. | Before: u = [RPM, Idc_f], y = [Vbatt, SOC, RPM] (Ibatt missing!). After: u = [RPM, MotorCurrent], y = [Vbatt, Ibatt]. | Regenerated model in EV_BlackBox_SysID_FINAL.mat: inputs u = [RPM, MotorCurrent] and outputs y = [Vbatt, Ibatt]. SOC handled via Coulomb counting; RPM removed from outputs. | TC-SYSID-MAP; Inspect EV_BlackBox_SysID_FINAL.mat signal labels and verify matrix dimensions | Threshold: Inputs and outputs match battery digital twin mandate (Vbatt, Ibatt predicted). Actual: Verified u = [2x1], y = [2x1]. | PASS | Temperature excluded because physical model lacks thermal dynamics (isothermal).
ISSUE-07 | Phase 2 | CRITICAL (SysID Fix & Variance) | SysID Fit Calculation & Negative Fit | Legacy report claimed NRMSE fit -2158.9% and validation Ibatt RMSE was 30.9 A (124% error). | EV_SysID_Auto.m, EV_BlackBox_SysID_FINAL.mat, EV_BlackBox_SysID_FINAL_REPORT.txt | 1) Legacy extraction bug: compare() 3rd output (x0 initial state) was mistakenly read as fit percentage. 2) Variance collapse: During steady hold, Vbatt std is only 0.015 V, driving NRMSE denominator to 0 and yielding -50.2%. 3) Strictly proper model (D=0) forced algebraic inverter current into state dynamics, overshooting to 67 A on load step (t=0.280 s) and causing Ibatt RMSE = 30.9 A. | Reported negative fit gave impression model was invalid; strictly proper model exhibited large transient overshoot. | Before: Ibatt RMSE = 30.9 A (peaked at 67 A), Vbatt RMSE = 0.3441 V. After: Ibatt RMSE = 2.06 A (93.3% reduction, <9% relative error), Vbatt RMSE = 0.0229 V (22.9 mV, 93.3% reduction). | 1) Removed normalization data leakage (parameters computed strictly on estimation slice 1:280). 2) Removed -100% score clipping; ranked models by normalized validation error. 3) Enabled direct feedthrough (Feedthrough = 1) in n4sid, allowing D matrix to absorb instantaneous current. | TC-SYSID-VAL; Run EV_SysID_Auto.m in MATLAB R2024b, evaluate physical RMSE/MAE on validation slice (0.280 to 0.400 s) | Threshold: Vbatt RMSE <= 0.50 V, Ibatt RMSE <= 5.0 A. Actual: Vbatt RMSE = 0.0229 V, Ibatt RMSE = 2.06 A. | PASS | Validation dataset has low dynamic excitation during steady-state hold; multi-step drive cycle recommended for wider excitation.
ISSUE-08 | Phase 4 | HIGH (Open Parameter Gap) | Battery Cell Resistance Modeling | Pack internal resistance is ~11.05 mOhm, representative of a 27 Ah cell template rather than the 5 Ah Samsung 50E cell. | +Batteries2/+ParallelAssemblies/ParallelAssemblyType1.ssc (L20-22), BLDCSpeedControlData.m (L47-51) | Pack was built in Simscape Battery Builder using a 27 Ah cell template (R0 ~ 8.5 mOhm). Changing AHCell = 5 Ah adjusted capacity, but the resistance lookup table remained that of the 27 Ah cell. | Voltage sag is underestimated under a 26 A discharge (0.25 V modeled vs 0.75-0.95 V physical). | Modeled: Rpack = 1.3 * 8.5 mOhm = 11.05 mOhm (sag 0.25 V). Physical Samsung 50E: Rpack ~ 1.3 * 28 mOhm ~ 36.4 mOhm (sag ~ 0.83 V). | Discrepancy documented and modeled vs datasheet values compared in Datasheet_vs_Simulation_Values.xlsx and BASELINE_INVENTORY.md. Active model retained with documented caveat to avoid breaking validated baseline. | TC-BATT-IR; Datasheet impedance comparison & Simscape SSC inspection | Documented parameter provenance and sag discrepancy analysis. | NOT VERIFIED | Re-synthesis in Simscape Battery Builder required to insert Samsung 50E lookup table and validate dynamic sag.
ISSUE-09 | Phase 2 | LOW (Audit Honesty) | Missing Reference & Thermal Signals | rpm_ref and cell temperature are reported as NOT_AVAILABLE in signal map. | BLDCSpeedControl_EV_Layout_v2.slx, EV_DAQ_Builder_V7.m (signal map L2350) | Physical model does not include thermal dynamics (isothermal at 293.15 K). Speed reference was not wired to logger block. | Signals could not be logged, but were previously reported without clear status. | Before: Ambiguity whether temperature was simulated. After: Confirmed isothermal model; temperature explicitly excluded from black-box twin. | Honest reporting confirmed: NOT_AVAILABLE reported without fabricating synthetic temperature data. Documented in EV_SysID_Signal_Mapping.md. | TC-SIG-MAP; Signal map inspection in EV_DAQ_Builder_V7.m | Threshold: No fabricated data. Actual: NOT_AVAILABLE reported honestly. | PASS | Thermal equivalent circuit (Foster/Cauer network) required to predict battery heating.
ISSUE-10 | Phase 6 | HIGH (Architectural Honesty) | Closed-Loop Digital Twin Integration | Project claimed to be a real-time closed-loop digital twin, but state-space model was executed offline after simulation ended. | BLDCSpeedControl_EV_Layout_v2.slx, EV_Twin_App.m | Unidirectional data flow (simulation -> DAQ CSV -> SysID MAT). Bidirectional feedback into Simulink plant is not implemented. | Inflated claims of closed-loop adaptive control. | Before: Claim of Level 3 closed-loop twin. After: Formally certified as Level 2 Digital Shadow. | Retracted production-readiness claim. Formally reclassified architecture as a Validated Level 2 Digital Shadow. Documented in EV_Digital_Twin_FINAL_AUDIT.md. | TC-ARCH-01; Simulink diagram architecture and callback inspection | Threshold: Accurate architectural classification. Actual: Certified Level 2 Digital Shadow. | PASS | Real-time closed-loop state feedback into motor inverter reserved for future work.
ISSUE-11 | Phase 3 | HIGH (Open Parameter Gap) | Motor Stator Resistance & Inductance | Simulink model phase resistance Rs = 0.10 Ohm is 4.65x higher than datasheet (0.0215 Ohm phase). | BLDCSpeedControlData.m (L32-34), Nanotec APBA80L048030-E datasheet | Datasheet specifies line-to-line resistance R_ll = 0.043 Ohm (Wye connected -> R_phase = 0.0215 Ohm) and L_ll = 0.21 mH (Ls - Ms = 0.105 mH). Model used legacy MathWorks values Rs = 0.10 Ohm and L_ll = 0.14 mH. | Stator copper losses are overestimated in simulation. | Modeled: Rs = 0.10 Ohm, L_ll = 0.14 mH. Datasheet: R_phase = 0.0215 Ohm, L_ll = 0.21 mH. | Reconciled and documented in Datasheet_vs_Simulation_Values.xlsx and BASELINE_INVENTORY.md. Changing Rs in Simulink without re-tuning PI speed/current loops induces chattering. Marked NOT VERIFIED in active simulation. | TC-MOTOR-PARAM; Datasheet comparison and electrical time constant calculation | Threshold: Mathematical conversion verified. Actual: Equations documented; active model parameter change marked NOT VERIFIED. | NOT VERIFIED | Updating Rs in Simulink requires re-tuning PI speed and current controller gains.
ISSUE-12 | Phase 2 | MEDIUM (Model Order) | Confirm Model Order and Sample Time | Legacy root model used six states (nx = 6), whereas newer script selected two states (nx = 2). | EV_SysID_Auto.m, EV_BlackBox_SysID.mat, EV_BlackBox_SysID_FINAL_REPORT.txt | Order 6 suffered from severe over-parameterization on 0.4s run, causing ill-conditioned matrices. Order 2 captures the dominant battery dynamics stably with minimal validation error. | Model order inconsistency across codebase. | Before: Inconsistency between nx = 6 (root MAT) and nx = 2. After: Unified nx = 2, Ts = 1.0 ms across code, report, and MAT files. | Confirmed nx = 2 and Ts = 1 ms based on order sweep (nx = 1..6) and discrete pole stability (¦lambda_1¦ = 0.7733, ¦lambda_2¦ = 0.4053 < 1.0). Documented in EV_BlackBox_SysID_FINAL_REPORT.txt. | TC-ORDER-SWEEP; Order sweep nx = 1..6 via EV_SysID_Auto.m; Run ID EV_RUN_20261021_161504 | Threshold: Max pole magnitude ¦lambda¦ < 1.0, stable order. Actual: ¦lambda¦ = 0.7733 < 1.0. | PASS | Multi-minute drive cycles needed to identify slow electrochemical diffusion states.
ISSUE-13 | Phase 3 | HIGH (Schedule Enforcement) | Simulation Stop-Time & Test Schedule | Parameter file had t_stop = 0.3, leaving only 20 ms hold after load ramp ended at 0.280 s. | RunAll.m, BLDCSpeedControlData.m | Test schedule has distinct phases: Startup (0-0.05 s), Speed ramp (0-0.227 s), Load ramp (0.230-0.280 s), and Steady hold (0.280-0.400 s). Stopping before 0.350 s truncates the steady hold. | Premature cutoff in 0.20s/0.30s runs caused false-negative V&V failures. | Before: t_stop = 0.3 s in parameter script. After: Default t_stop = 0.4 s enforced; short runs blocked in validation mode. | Default t_stop = 0.4 s configured in BLDCSpeedControlData.m. Added FullValidation stop-time check (t_stop >= 0.350 s; benchmark 0.400 s) in RunAll.m throwing RunAll:InsufficientDuration if too short. Added separate DiagnosticMode. | VV-000; RunAll execution check with t_stop = 0.400 s and short run validation | Threshold: t_stop >= 0.400 s enforced. Actual: 0.400 s completed. | PASS | Extended thermal simulation requires separate duration profile.
ISSUE-14 | Phase 4 | MEDIUM (Sign & Capacity) | Battery Voltage, Capacity, SOC & Signs | Potential confusion between nominal (48.1V) and max (54.6V) voltage, Simscape negative current vs engineering positive discharge, and SOC integration accuracy. | Simscape Battery pack (Batteries2.slx), EV_DAQ_Builder_V7.m (L2380-2395) | Simscape uses passive sign convention (inward current positive = charging), requiring sign inversion for EV discharge engineering convention. | Sign errors would cause negative energy and inverted SOC calculations. | Integrated current = 6.4264 A*s = 0.001785 Ah. Theoretical delta SOC = 0.00003570. Reported delta SOC = 0.00003560. Coulomb ratio = 0.9971 (99.71% match). | Verified 13S10P topology (130 cells, 50 Ah capacity). Confirmed sign conversion in DAQ (abs(BatteryCurrent)). Verified Coulomb counting accuracy (ratio = 0.9971, VV-011 PASS). | VV-011; Compare delta SOC from battery block against int(Ibatt dt) / (3600 * 50 Ah); Run ID EV_RUN_20261021_161504 | Threshold: Ratio 0.80 <= Ratio <= 1.25. Actual: 0.9971 (PASS). | PASS | Cell self-discharge not modeled over 0.4s window.
ISSUE-15 | Phase 5 | HIGH (Signal Conditioning) | DAQ Pipeline & Time Alignment | PWM switching ripple and variable-step solver outputs created noisy raw data with non-uniform time steps. | EV_DAQ_Builder_V7.m (L2300-2450), Raw_Archive files | High-frequency inverter switching (10 kHz) introduces massive ripple that distorts steady-state averages if not filtered uniformly. | Aliasing and corrupted steady-state metrics in raw logs. | Before: Raw variable-step logger data with 10 kHz PWM spikes. After: Clean 1 kHz uniform time series (401 samples, zero NaNs, aligned channels). | Verified 1 ms moving-window uniform resampling and ripple averaging in EV_DAQ_Builder_V7.m. Checked for zero NaNs, zero dropped samples, and exact column mapping. | TC-DAQ-CLEAN; Inspect EV_FINAL_RESULTS.csv and verify 401 rows, 1 ms uniform spacing, 0 NaNs | Threshold: 1 ms uniform time step, zero NaNs. Actual: Exactly 1.0 ms step (0 to 0.400 s), 0 NaNs. | PASS | 1 ms window limits identification bandwidth to <= 500 Hz.
ISSUE-16 | Phase 5 | HIGH (V&V Completeness) | Rebuild & Verify V&V Checks | Baseline report claimed 21 PASS and 3 FAIL out of 25 checks, with ambiguity regarding the 25th check. | EV_DAQ_Builder_V7.m (L2559-2564), EV_VV_FINAL_RESULTS.xlsx | Check VV-015 was skipped completely in EV_DAQ_Builder_V7.m (jumping from VV-014 to VV-016). There are exactly 24 individual checks (21 PASS, 3 FAIL). Row 25 in the summary table was the composite summary row OVERALL. | Ambiguous check count in baseline documentation. | Before: Unexplained missing check ID; ambiguous 25 total. After: Exactly 24 active checks + composite OVERALL row documented; 21 PASS, 3 FAIL. | Complete 24-check register authored in sheet Comprehensive_VV_Register of EV_VV_FINAL_RESULTS.xlsx with formulas, units, signals, windows, limits, actual results, status, and supporting evidence. The 3 failing checks (VV-008, VV-012, VV-023) are honestly maintained and justified by physical powertrain damping friction (+0.30 A) and filter lag (+0.006 ratio). | TC-VV-AUDIT; Full V&V audit across all 24 individual checks and composite row; Run ID EV_RUN_20261021_161504 | Threshold: Every status supported by reproducible calculation. Actual: 21 PASS, 3 FAIL documented in Comprehensive_VV_Register. | PASS | Re-tuning thresholds or load scaling required for 100% green dashboard.
ISSUE-17 | Phase 7 | MEDIUM (Documentation Sync) | Synchronize Audit Report & Excel Register | Discrepancies between narrative markdown report and Excel register in issue numbering, severities, and metrics. | EV_Digital_Twin_FINAL_AUDIT.md, EV_Digital_Twin_ROOT_CAUSE_REGISTER_FINAL.xlsx, FINAL_VALIDATION_SUMMARY.md | Independent updates to different documents caused desynchronization of issue IDs and statuses. | Inconsistent evidence presentation across reports. | Before: Desynchronized issue lists and mismatched statuses. After: 100% 1-to-1 sync across all documents. | 100% synchronization established across all 18 issues (ISSUE-00 to ISSUE-17) across EV_Digital_Twin_ROOT_CAUSE_REGISTER_FINAL.xlsx, EV_Digital_Twin_FINAL_AUDIT.md, FINAL_VALIDATION_SUMMARY.md, UNRESOLVED_ISSUES.md, and CHANGELOG.md. | TC-DOC-SYNC; Cross-document reconciliation and schema matching | Threshold: Exact 1-to-1 matching of IDs, descriptions, and statuses. Actual: Fully synchronized. | PASS | None.